## Лист1
WBS number | Task description | Estimates | Particular task | Library chosen
1 | Implement File Manager application | 129 h | UI | Qt
1.1 | Derive application to Logic and GUI | 75 h | Threading | Qt
2 | Design MainWindow class (controller) | 6 h
2.1 | Design the UI of the application | 3.5 h
2.1.1 | Create two windows(like in Total commander), which are represented by QTreeView | 0.5 h
2.1.2 | Add necessary buttons(Copy, Move, Insert, etc.) | 1 h
2.1.3 | Add necessary text edits | 1 h
2.1.4 | Add necessary spasers | 0.5 h
2.1.5 | Add necessary layouts | 0.5 h
2.2 | Add UiHandler object and FileModelHandler object as private fields of MainWindow class | 0.5 h
2.3 | Connect signals from UI elements with app logic | 1 h
2.4 | Handle event filter | 1 h
3 | Design UiHandler class (view) | 38.5 h
3.1 | It should set up ui, created earlier | 1 h
3.2 | It should show a catalogue inside every window | 1.5 h
3.3 | It should show an appropriate icon for different file types | 1 h
3.4 | It should have the ability to show/hide some file attributes | 2 h
3.5 | It should have the ability to sort files by name, size etc. | 3 h
3.6 | It should support file/folders rename operations | 1 h
3.7 | It should set two instanses of FileModelHandler class to QTreeViews, created in ui | 1 h
3.8 | It should handle which of the QTreeViews is active before perfoming an action(like copy, etc.) | 3 h
3.9 | It should show progress bar during the operation | 5 h
3.10 | It should get proper index of selected item in particular QTreeView | 4 h
3.11 | It should handle drag and drop operations | 5 h
3.12 | it should operate with threads, to implement non-blocking UI | 9 h
3.13 | It should show gialogs to user, so that the user confirm his action(deleting, etc.) | 2 h
4 | Design FileModelHandler class (model) | 15.5 h
4.1 | It should contain two QFileSystemModel objects | 0.5 h
4.2 | It should instantiate QFileSystemModel objects, provide a path and ReadWriteMode, etc. | 1 h
4.3 | It should store current active side, chosen by user and got at UiHandle, to know which QFileSystemModel to operate on | 3 h
4.4 | It should store chosen action type, to know what to do with the selected item(copy or move, etc.) | 1 h
4.5 | It should be able to make directory according to index, given by view | 5 h
4.6 | It should be able to delete an item or directory according to index, given by view | 3 h
4.7 | It should initiate copy, to know what to do with the previously selected item after user presses Insert button | 1 h
4.8 | It should initiate move operation, to know what to do with the previously selected item after user presses Insert button | 1 h
5 | Make design improvements | 15 h
6 | Create UML diagrams | 2 h
7 | Implement designed model/view architecture | 30 h
8 | Handle cross-compile issues | 5 h
9 | Create “make” file to compile application | 6 h
10 | Create compiled executables | 1 h
11 | Create requirements specification | 5 h
12 | Create application modules description | 5 h